## Dashboard
🍵 KOMBUCHA BREWERY ¦ PRODUCTION PLANNING DASHBOARD
Generated: March 15, 2026 05:23
Total Batches | On Schedule | At Risk | Unassigned | Alerts | Low Stock Items
14 | 6 | 8 | 0 | 13 | 0
Flavor | Batch (L) | Tank | Ferm. Start | Ferm. End | Bottling Date | Bottles | Status
Original Kombucha | 200 | T-01 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 563 | ON_SCHEDULE
Original Kombucha | 200 | T-02 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 563 | ON_SCHEDULE
Original Kombucha | 200 | T-07 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 563 | ON_SCHEDULE
Original Kombucha | 200 | T-08 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 563 | ON_SCHEDULE
Original Kombucha | 200 | T-03 | 2026-03-18 | 2026-03-28 | 2026-03-29 | 563 | ON_SCHEDULE
Original Kombucha | 100.5 | T-04 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 283 | ON_SCHEDULE
Ginger Lemon | 200 | T-01 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 563 | AT_RISK_LATE
Ginger Lemon | 200 | T-02 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 563 | AT_RISK_LATE
Ginger Lemon | 61.5 | T-05 | 2026-03-20 | 2026-03-30 | 2026-03-31 | 173 | AT_RISK_LATE
Mango Turmeric | 200 | T-07 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 563 | AT_RISK_LATE
Mango Turmeric | 190.5 | T-08 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 536 | AT_RISK_LATE
Blueberry Lavender | 200 | T-03 | 2026-03-28 | 2026-04-07 | 2026-04-08 | 563 | AT_RISK_LATE
Blueberry Lavender | 119.5 | T-04 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 336 | AT_RISK_LATE
Raspberry Rose | 142 | T-05 | 2026-03-30 | 2026-04-09 | 2026-04-10 | 400 | AT_RISK_LATE

## Orders
📋 CUSTOMER ORDERS & DEMAND
Order_ID | Flavor | Quantity_Bottles | Due_Date | Priority | Customer
ORD-001 | Original Kombucha | 1500 | 2026-03-29 | 1 | Whole Foods Chicago
ORD-002 | Ginger Lemon | 800 | 2026-03-27 | 2 | Fresh Market Peoria
ORD-003 | Blueberry Lavender | 600 | 2026-04-02 | 3 | Natural Grocers
ORD-004 | Raspberry Rose | 400 | 2026-04-04 | 3 | Midwest Co-op
ORD-005 | Original Kombucha | 1000 | 2026-04-05 | 1 | Jewel-Osco
ORD-006 | Ginger Lemon | 500 | 2026-04-09 | 2 | Target Grocery
ORD-007 | Mango Turmeric | 700 | 2026-03-31 | 2 | Fresh Thyme
ORD-008 | Blueberry Lavender | 300 | 2026-04-06 | 3 | Green Earth Market
ORD-009 | Original Kombucha | 600 | 2026-04-14 | 1 | Sam's Club
ORD-010 | Mango Turmeric | 400 | 2026-04-12 | 2 | Sprouts

## Inventory
🧪 INGREDIENT & PACKAGING INVENTORY
Material_ID | Material_Name | Stock_Level | Unit | Safety_Stock | Reorder_Point | Lead_Time_Days | Cost_Per_Unit
MAT-001 | Green Tea (kg) | 45 | kg | 10 | 15 | 5 | 8.5
MAT-002 | Black Tea (kg) | 30 | kg | 8 | 12 | 5 | 6
MAT-003 | Cane Sugar (kg) | 80 | kg | 20 | 30 | 3 | 1.2
MAT-004 | SCOBY Starter Culture | 12 | qty | 3 | 5 | 7 | 25
MAT-005 | Ginger Extract (L) | 8 | L | 2 | 4 | 4 | 45
MAT-006 | Lemon Juice (L) | 15 | L | 3 | 5 | 3 | 12
MAT-007 | Blueberry Puree (kg) | 6 | kg | 2 | 4 | 6 | 18
MAT-008 | Lavender Extract (L) | 3 | L | 1 | 2 | 7 | 60
MAT-009 | Raspberry Puree (kg) | 9 | kg | 2 | 4 | 5 | 20
MAT-010 | Rose Water (L) | 4 | L | 1 | 2 | 7 | 35
MAT-011 | Mango Puree (kg) | 10 | kg | 3 | 5 | 5 | 15
MAT-012 | Turmeric Powder (kg) | 2 | kg | 0.5 | 1 | 4 | 22
MAT-013 | Glass Bottles (500mL) | 4800 | qty | 500 | 1000 | 7 | 0.45
MAT-014 | Bottle Caps | 5000 | qty | 500 | 1000 | 5 | 0.02
MAT-015 | Labels | 4500 | qty | 500 | 800 | 4 | 0.08
MAT-016 | Filtered Water (L) | 5000 | L | 500 | 800 | 1 | 0.005

## Recipe_BOM
📐 RECIPE / BILL OF MATERIALS (BOM)
Flavor | Ingredient | Quantity_Per_Batch | Unit | Notes
Original Kombucha | Green Tea (kg) | 2 | kg | First fermentation base
Original Kombucha | Cane Sugar (kg) | 16 | kg | 7–8% sugar by volume
Original Kombucha | SCOBY Starter Culture | 1 | qty | 1 SCOBY per 200L batch
Original Kombucha | Filtered Water (L) | 180 | L | Reverse osmosis
Original Kombucha | Glass Bottles (500mL) | 400 | qty | 200L ÷ 0.5L bottle
Original Kombucha | Bottle Caps | 400 | qty | One per bottle
Original Kombucha | Labels | 400 | qty | Brand labels
Ginger Lemon | Green Tea (kg) | 2 | kg | Base tea
Ginger Lemon | Cane Sugar (kg) | 15 | kg | Slightly less sweet
Ginger Lemon | SCOBY Starter Culture | 1 | qty | 1 SCOBY per batch
Ginger Lemon | Ginger Extract (L) | 4 | L | 2F flavor addition
Ginger Lemon | Lemon Juice (L) | 6 | L | Fresh pressed
Ginger Lemon | Filtered Water (L) | 180 | L
Ginger Lemon | Glass Bottles (500mL) | 400 | qty
Ginger Lemon | Bottle Caps | 400 | qty
Ginger Lemon | Labels | 400 | qty
Blueberry Lavender | Black Tea (kg) | 2 | kg | Richer base
Blueberry Lavender | Cane Sugar (kg) | 15 | kg
Blueberry Lavender | SCOBY Starter Culture | 1 | qty
Blueberry Lavender | Blueberry Puree (kg) | 8 | kg | 2F addition
Blueberry Lavender | Lavender Extract (L) | 1.5 | L | 2F addition
Blueberry Lavender | Filtered Water (L) | 175 | L
Blueberry Lavender | Glass Bottles (500mL) | 400 | qty
Blueberry Lavender | Bottle Caps | 400 | qty
Blueberry Lavender | Labels | 400 | qty
Raspberry Rose | Black Tea (kg) | 2 | kg
Raspberry Rose | Cane Sugar (kg) | 14 | kg
Raspberry Rose | SCOBY Starter Culture | 1 | qty
Raspberry Rose | Raspberry Puree (kg) | 7 | kg | 2F addition
Raspberry Rose | Rose Water (L) | 2 | L | 2F addition
Raspberry Rose | Filtered Water (L) | 175 | L
Raspberry Rose | Glass Bottles (500mL) | 400 | qty
Raspberry Rose | Bottle Caps | 400 | qty
Raspberry Rose | Labels | 400 | qty
Mango Turmeric | Green Tea (kg) | 2 | kg
Mango Turmeric | Cane Sugar (kg) | 14 | kg
Mango Turmeric | SCOBY Starter Culture | 1 | qty
Mango Turmeric | Mango Puree (kg) | 9 | kg | Alphonso mango
Mango Turmeric | Turmeric Powder (kg) | 0.5 | kg | Anti-inflammatory
Mango Turmeric | Filtered Water (L) | 175 | L
Mango Turmeric | Glass Bottles (500mL) | 400 | qty
Mango Turmeric | Bottle Caps | 400 | qty
Mango Turmeric | Labels | 400 | qty

## Fermentation_Tanks
🏭 FERMENTATION TANK INVENTORY
Tank_ID | Capacity_Liters | Status | Available_Date | Material | Temperature_Control | Notes
T-01 | 200 | Available | 2026-03-15 | Stainless Steel 304 | Yes | Primary fermentation
T-02 | 200 | Available | 2026-03-15 | Stainless Steel 304 | Yes | Primary fermentation
T-03 | 200 | In Use | 2026-03-18 | Stainless Steel 304 | Yes | Currently fermenting Original
T-04 | 150 | Available | 2026-03-15 | Stainless Steel 316 | Yes | Small batch specialty
T-05 | 150 | In Use | 2026-03-20 | Stainless Steel 316 | Yes | Currently fermenting Ginger
T-06 | 100 | Maintenance | 2026-03-22 | Polyethylene HDPE | No | Scheduled maintenance until +7d
T-07 | 200 | Available | 2026-03-15 | Stainless Steel 304 | Yes | Secondary/flavor tank
T-08 | 200 | Available | 2026-03-15 | Stainless Steel 304 | Yes | Secondary/flavor tank

## Bottling_Line
🍾 BOTTLING LINE CAPACITY
Line_ID | Line_Name | Bottles_Per_Hour | Operating_Hours_Per_Day | Daily_Capacity | Status | Notes
BL-01 | Main Bottling Line | 300 | 8 |  | Active | Automated rinse-fill-cap
BL-02 | Secondary Line | 150 | 6 |  | Active | Semi-automated
BL-03 | Label Application | 500 | 8 |  | Active | Automated label applicator

## Production_Plan
Date | Flavor | Batch_Size_Liters | Assigned_Tank | Fermentation_Start | Fermentation_End | Bottling_Date | Actual_Bottling_Date | Bottles_Planned | Due_Date | Priority | Status
2026-03-15 | Original Kombucha | 200 | T-01 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 563 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Original Kombucha | 200 | T-02 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 563 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Original Kombucha | 200 | T-07 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 563 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Original Kombucha | 200 | T-08 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 563 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Original Kombucha | 200 | T-03 | 2026-03-18 | 2026-03-28 | 2026-03-29 | 2026-03-29 | 563 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Original Kombucha | 100.5 | T-04 | 2026-03-15 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 283 | 2026-03-29 | 1 | ON_SCHEDULE
2026-03-15 | Ginger Lemon | 200 | T-01 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 563 | 2026-03-27 | 2 | AT_RISK_LATE
2026-03-15 | Ginger Lemon | 200 | T-02 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 563 | 2026-03-27 | 2 | AT_RISK_LATE
2026-03-15 | Ginger Lemon | 61.5 | T-05 | 2026-03-20 | 2026-03-30 | 2026-03-31 | 2026-03-31 | 173 | 2026-03-27 | 2 | AT_RISK_LATE
2026-03-15 | Mango Turmeric | 200 | T-07 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 563 | 2026-03-31 | 2 | AT_RISK_LATE
2026-03-15 | Mango Turmeric | 190.5 | T-08 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 536 | 2026-03-31 | 2 | AT_RISK_LATE
2026-03-15 | Blueberry Lavender | 200 | T-03 | 2026-03-28 | 2026-04-07 | 2026-04-08 | 2026-04-08 | 563 | 2026-04-02 | 3 | AT_RISK_LATE
2026-03-15 | Blueberry Lavender | 119.5 | T-04 | 2026-03-25 | 2026-04-04 | 2026-04-05 | 2026-04-05 | 336 | 2026-04-02 | 3 | AT_RISK_LATE
2026-03-15 | Raspberry Rose | 142 | T-05 | 2026-03-30 | 2026-04-09 | 2026-04-10 | 2026-04-10 | 400 | 2026-04-04 | 3 | AT_RISK_LATE

## Actual_Production
📊 ACTUAL PRODUCTION LOG
Date | Flavor | Assigned_Tank | Produced_Bottles | Waste_Bottles | Yield_Pct | Remarks
2026-03-13 | Original Kombucha | T-03 | 390 | 10 |  | Slight over-carbonation on 10 bottles
2026-03-12 | Ginger Lemon | T-05 | 395 | 5 |  | Production within spec
2026-03-10 | Blueberry Lavender | T-01 | 380 | 20 |  | Seal issue on line BL-02 — corrected

## README
KOMBUCHA BREWERY — PRODUCTION PLANNING AI AGENT
Industrial Engineering Portfolio Project
HOW TO USE THIS WORKBOOK
1. Review and update the 'Orders' sheet with current customer demand.
2. Update 'Inventory' with current stock levels.
3. Check 'Fermentation_Tanks' — update Status and Available_Date.
4. Run the Python agent: python kombucha_agent.py
5. The agent will populate: Production_Plan, Dashboard, Bottleneck_Report, Ingredient_Alerts.
SHEETS OVERVIEW
Orders → Customer demand and due dates
Inventory → Raw material and packaging stock
Recipe_BOM → Bill of materials per flavor
Fermentation_Tanks → Tank capacity and availability
Bottling_Line → Line capacity constraints
Production_Plan → AUTO-GENERATED brewing schedule
Actual_Production → Manual production log
Dashboard → AUTO-GENERATED KPI dashboard
Bottleneck_Report → AUTO-GENERATED insights & alerts
Ingredient_Alerts → AUTO-GENERATED shortage alerts
KEY PARAMETERS (edit in kombucha_agent.py)
LITERS_PER_BOTTLE = 0.355 (12 oz standard bottle)
FERMENTATION_DAYS = 10 (adjust for your process)
PLANNING_HORIZON = 21 (days to plan ahead)

## Bottleneck_Report
🔍 BOTTLENECK & INSIGHTS REPORT
# | Category | Severity | Message
1 | TANK_STATUS | INFO | Tank T-03 will become available on 2026-03-18.
2 | TANK_STATUS | INFO | Tank T-05 will become available on 2026-03-20.
3 | TANK_STATUS | INFO | Tank T-06 will become available on 2026-03-22.
4 | INGREDIENT_SHORTAGE | HIGH | 🔴 SHORTAGE: 'Cane Sugar (kg)' needs 96.0 kg but only 80 in stock (short by 16.0)
5 | INGREDIENT_SHORTAGE | HIGH | 🔴 SHORTAGE: 'Ginger Extract (L)' needs 12.0 L but only 8 in stock (short by 4.0)
6 | INGREDIENT_SHORTAGE | HIGH | 🔴 SHORTAGE: 'Lemon Juice (L)' needs 18.0 L but only 15 in stock (short by 3.0)
7 | INGREDIENT_SHORTAGE | HIGH | 🔴 SHORTAGE: 'Mango Puree (kg)' needs 18.0 kg but only 10 in stock (short by 8.0)
8 | INGREDIENT_SHORTAGE | HIGH | 🔴 SHORTAGE: 'Blueberry Puree (kg)' needs 16.0 kg but only 6 in stock (short by 10.0)
9 | LATE_ORDER_RISK | HIGH | ⚠️ Ginger Lemon batch (due 2026-03-27) will bottle on 2026-04-05 – AT RISK of being late.
10 | LATE_ORDER_RISK | HIGH | ⚠️ Ginger Lemon batch (due 2026-03-27) will bottle on 2026-04-05 – AT RISK of being late.
11 | LATE_ORDER_RISK | HIGH | ⚠️ Ginger Lemon batch (due 2026-03-27) will bottle on 2026-03-31 – AT RISK of being late.
12 | LATE_ORDER_RISK | HIGH | ⚠️ Mango Turmeric batch (due 2026-03-31) will bottle on 2026-04-05 – AT RISK of being late.
13 | LATE_ORDER_RISK | HIGH | ⚠️ Mango Turmeric batch (due 2026-03-31) will bottle on 2026-04-05 – AT RISK of being late.
14 | LATE_ORDER_RISK | HIGH | ⚠️ Blueberry Lavender batch (due 2026-04-02) will bottle on 2026-04-08 – AT RISK of being late.
15 | LATE_ORDER_RISK | HIGH | ⚠️ Blueberry Lavender batch (due 2026-04-02) will bottle on 2026-04-05 – AT RISK of being late.
16 | LATE_ORDER_RISK | HIGH | ⚠️ Raspberry Rose batch (due 2026-04-04) will bottle on 2026-04-10 – AT RISK of being late.

## Ingredient_Alerts
🧪 INGREDIENT SHORTAGE & LOW STOCK ALERTS
# | Type | Material | Flavor | Qty_Needed | Stock | Shortage
1 | SHORTAGE | Cane Sugar (kg) | Original Kombucha | 96 | 80 | 16
2 | SHORTAGE | Ginger Extract (L) | Ginger Lemon | 12 | 8 | 4
3 | SHORTAGE | Lemon Juice (L) | Ginger Lemon | 18 | 15 | 3
4 | SHORTAGE | Mango Puree (kg) | Mango Turmeric | 18 | 10 | 8
5 | SHORTAGE | Blueberry Puree (kg) | Blueberry Lavender | 16 | 6 | 10